## Home
Tasks Name | Start Build | Finish Build | % Build | Assignee | Start Testing | Finish Testing | % Testing | Assignee | Notes | Link đề bài
Header | 2023-06-13 | 2023-06-21 | 100% | Anh
Logo | 2023-06-13 | 2023-06-15 | 100% | Anh
Navbar | 2023-06-13 | 2023-06-21 | 100% | Anh
Submenu | 2023-06-13 | 2023-06-21 | 100% | Anh
Search form | 2023-06-14 | 2023-06-15 | 100% | Anh
Banner | 2023-06-14 | 2023-06-15 | 100% | Anh
Why | 2023-06-21 | 2023-06-21 | 100% | Hùng
About | 2023-06-21 | 2023-06-21 | 100% | Hùng
Numbers | 2023-06-21 | 2023-06-21 | 100% | Hùng
Blog | 2023-06-21 | 2023-06-29 | 100% | Anh
Q&A | 2023-06-21 | 2023-06-29 | 100% | Anh
Featured | 2023-06-21 |  | 90% | Hùng
Clients | 2023-06-26 | 2023-06-29 | 100% | Anh
Ready | 2023-06-21 | 2023-06-24 | 100% | Hùng
Footer | 2023-06-21 | 2023-06-21 | 100% | Hùng
Back to top | 2023-06-26 | 2023-06-29 | 100% | Anh

## About
Tasks Name | Start Build | Finish Build | % Build | Assignee | Start Testing | Finish Testing | % Testing | Assignee | Notes
About page | 2023-07-02 | 2023-07-05 | 100% | Anh

## Service
Tasks Name | Start Build | Finish Build | % Build | Assignee | Start Testing | Finish Testing | % Testing | Assignee | Notes
Service page | 2023-07-05 | 2023-07-07 | 100% | Anh

## Blog Posts
Tasks Name | Start Build | Finish Build | % Build | Assignee | Start Testing | Finish Testing | % Testing | Assignee | Notes
Blog Posts | 2023-07-05 | 2023-07-07 | 100%
Categories: 1. Business 2. Design 3. Industry 4. Programming | 2023-07-08 | 2023-07-08 | 100% | Anh
Main blog - first page | 2023-07-05 | 2023-07-08 | 100% | Hùng
Main blog - second page | 2023-07-05 | 2023-07-08 | 100% | Hùng
Main blog - third page | 2023-07-05 | 2023-07-08 | 100% | Hùng
Sub blog - The best choice | 2023-07-05 | 2023-07-08 | 100% | Hùng
Sub blog - Hello world | 2023-07-05 | 2023-07-08 | 100% | Hùng
Sub blog - Hello world 2 | 2023-07-05 | 2023-07-08 | 100% | Hùng
Sub blog - Corporate Business | 2023-07-05 | 2023-07-08 | 100% | Hùng
Sub blog - Corporate Business 2 | 2023-07-05 | 2023-07-08 | 100% | Anh
Sub blog - Corporate Business 3 | 2023-07-05 | 2023-07-08 | 100% | Anh
Sub blog - Programming | 2023-07-05 | 2023-07-08 | 100% | Hùng
Month: March 2021 | 2023-07-05 | 2023-07-08 | 100% | Anh
Page 1 | 2023-07-05 | 2023-07-08 | 100% | Anh
Page 2 | 2023-07-05 | 2023-07-08 | 100% | Anh
Page 3 | 2023-07-05 | 2023-07-08 | 100% | Anh
Landing Page | 2023-07-07 | 2023-07-07 | 100% | Anh
404 Page | 2023-07-05 | 2023-07-07 | 100% | Hùng

## Contact
Tasks Name | Start Build | Finish Build | % Build | Assignee | Start Testing | Finish Testing | % Testing | Assignee | Notes
Contact page | 2023-07-05 | 2023-07-07 | 100% | Hùng